## Requirement_Traceability_Matrix
REQUIREMENTS TRACEABILITY MATRIX
Project Name | Campus Lost and Found Portal
Project Type | Software Application Development
Project Start Date | 2025-09-11
Project End Date | 2025-12-05
Project Sponsor | Dr. Koorosh Firouzbakht
Primary Driver
Secondary Driver
Division | School of Computing and Data Science
Project Manager/Department | COMP 4960 - 01A - Team 2
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Architectural/Design Document | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
001 | 4.1.1 | Customer does not want random users being able to access the app that is intended solely for university students and staff | The system shall allow users to register an account using their Wentworth ID. | Completed | SDUI 4.3.1 | Firebase Authentication | React/SwiftUI/Firebase Authentication | Authentication Module | 1, 2 | iOS & Web | iOS & Web | Passed during testing and final demo
002 | 4.1.2 | All university students and staff should be able to access the app | The system shall allow all registered users access to the app’s services. | Completed | SDUI 4.3.1 | Firebase Authentication & Firestore validation | iOS App, Web App, Firebase, Firestore | Authentication Module & User Validation Module | N/A | iOS & Web | iOS & Web | Verified by attempting to access app
003 | 4.1.3 | App users need to submit reports for lost/found items | The system shall ask if the user wants to report a found or lost item. | Completed | SDUI 4.1.2 | Lost/Found selector | React/Swift UI | Lost/Found Selection Screen | N/A | iOS & Web | iOS & Web | User can choose lost or found before filling a report
004 | 4.1.4 | App users need to submit reports for lost/found items | The system shall allow the user to report a lost item. The user must report the item category, description, last known location, and their contact information. | Completed | SDUI 4.1.2.3 | Report Form | React/Swift UI/Firestore/Firebase | Lost item form & Firebase | 3, 4 | iOS & Web | iOS & Web | Complete form submits and appears for admin
005 | 4.1.4.1 | Item reports should contain enough details to uniquely identify an item | The system shall require the user to input the item’s category (e.g., backpack, coat, laptop). | Completed | SDUI 4.1.2.3 | Category Field | React/Swift UI/Firestore | Category specifications | N/A | iOS & Web | iOS & Web | Form cannot be submitted without a category
006 | 4.1.4.2 | Item reports should contain enough details to uniquely identify an item | The system shall require the user to report a description of the item. | Completed | SDUI 4.1.2.3 | Description Field | React/Swift UI/Firestore | Description text area | N/A | iOS & Web | iOS & Web | User can specify a description for the item
007 | 4.1.4.2.1 | Item reports should contain enough details to uniquely identify an item | The system shall require the user to to write a basic text description of the item. | Completed | SDUI 4.1.2.3 | Text Field | React/Swift UI/Firestore | Description text area | N/A | iOS & Web | iOS & Web | User can specify a description for the item
008 | 4.1.4.2.2 | Item reports should contain enough details to uniquely identify an item | The system shall allow users to optionally upload an image of their lost item. | Completed | SDUI 4.1.2.3 | Image Upload | React/Swift UI/Firebase | Image Upload | 6 | iOS & Web | iOS & Web | Image is successfuly uploaded and shows in the report
009 | 4.1.4.3 | Item reports should contain enough details to uniquely identify an item | The system shall require the user to report the last known location of their item. | Completed | SDUI 4.1.2.3 | Location Input | React/Swift UI | Location input | N/A | iOS & Web | iOS & Web | Location successfuly added and shows in the report
010 | 4.1.4.3.1 | Reports should indicate the location where the item was lost or found | The system shall allow users to mark the last known location of their item with a pin using their device’s GPS. | Completed | SDUI 4.1.2.3 | GPS Pin | SwiftUI/MapKit | GPS Pin | 8 | iOS & Web | iOS & Web | Pin correctly reflects location in iOS app
011 | 4.1.4.3.2 | Reports should indicate the location where the item was lost or found | The system shall allow users to optionally select the building in which their lost item was last seen. | Completed | SDUI 4.1.2.3 | GPS Pin/Description | React/SwiftUI | Location Specification | N/A | iOS & Web | iOS & Web | Users can correctly specifiy the building
012 | 4.1.4.4 | Reports should provide a method for the rightful owner to collect their item | The system shall require the user’s contact information. | Completed | SDUI 4.1.2.3 | Contact Field | React/SwiftUI | Contact info section | N/A | iOS & Web | iOS & Web | Reports show users contact information
013 | 4.1.4.4.1 | Reports should provide a method for the rightful owner to collect their item | The system shall require the user’s name. | Completed | SFR 2.1.4.4.1 | Contact Field | React/SwiftUI/Firebase Authentication | Name Section | N/A | iOS & Web | iOS & Web | Name is stored with the report
014 | 4.1.4.4.2 | Reports should provide a method for the rightful owner to collect their item | The system shall require the user’s phone number. | Completed | SFR 2.1.4.4.2 | Contact Field | React/SwiftUI | Phone number section | N/A | iOS & Web | iOS & Web | Phone number is stored with the report
015 | 4.1.5 | App users need to search and filter item reports to accurately identify their item | The system’s user interface shall display a search bar, for users to search through the list of found items. | Completed | SFR 2.1.5 | Search Bar | React/SwiftUI/Firestore | Searchbar | 5 | iOS & Web | iOS & Web | Functional search bar
016 | 4.2.1 | Customer does not want random users being able to access the app that is intended solely for university students and staff | The system shall restrict access to users with a valid Wentworth account. | Completed | SNFR 2.2.1 | Domain Restriction | Firebase Authentication | Authentication Module | 1, 2 | iOS & Web | iOS & Web | non @wit.edu users cannot log in
017 | 4.2.2 | App users need to submit reports for lost/found items | The report form shall include labeled fields for category, description and location. | Completed | SNFR 2.2.2 | Labeled Fields | React/SwiftUI | Form Labels | N/A | iOS & Web | iOS & Web | All required and optional fields are displayed
018 | 4.2.3 | App users should have access to current data in a timely manner | Lost and found item reports that are approved by an admin shall be visible to users in under 1 minute. | Completed | SNFR 2.2.3 | Real-time visibility | React/SwiftUI/Firestore | Admin Dashboard | 3 | iOS & Web | Database | Approved reports appear instantly
019 | 4.2.4 | Item reports should be stored securely and accessible by users on any platform | Previously found items shall be saved into a database. | Completed | SNFR 2.2.4 | Firestore Database capabilities | React/SwiftUI/Firestore | Firebase/Firestore | N/A | iOS & Web | iOS & Web | Reports remain available after app restarts
020 | 4.2.5 | Users want to protect their personal information and may be uncomfortable publishing their name and phone number to the entire university | User data and contact information shall only be visible to the item reporter and system administrators. | Not Started | SNFR 2.2.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A
021 | 4.2.6 | The app should be capable of storing a large amount of item reports because it will have thousands of users | The database shall have the capacity to store a minimum of 5000 lost and found item reports. | Completed | SNFR 2.2.6 | Firestore database | Firestore | Firestore Database | N/A | N/A | Database | Ensured by firestore
022 | 4.2.7 | Users may want to delete reports with errors or resolve them once their item is found or returned | The system shall allow users to view and delete their own reports. | Completed | SNFR 2.2.7 | App profile | React/SwiftUI/Firestore | User Profile | N/A | iOS & Web | iOS & Web | Users can view their reports in the app profile view.
023 | 4.2.8 | Users should be contacted in a timely manner if another user finds their item | The system shall send an email notification to a user when their reported lost item gets reported as found by another user. | Not Started | SNFR 2.2.8 | N/A | N/A | Email Notifications | 7 | N/A | N/A | N/A
024 | 4.3.1 | Having a native mobile app is beneficial for user experience on mobile devices | The system shall be built using Swift and Swift UI for the mobile application. | Completed | SOR 2.3.1 | Swift/SwiftUI | Swift/SwiftUI | Software Architecture | N/A | N/A | iOS | iOS app successfuly runs
025 | 4.3.2 | Having a web application allows for higher speed and productivity, especially for system moderators | The system shall be built using Node.js/Express backend with a Firebase database for the web app. | Completed | SOR 2.3.2 | Node.js/Firebase/Firestore integration | React/Tailwind/Node.js/Express | Software Architecture | N/A | N/A | Web | Web app successfuly runs
026 | 4.3.3 | Users may submit inappropriate content, so all reports should be reviewed by a moderator before they are published | The system shall have a separate system view for admins. | Completed | SOR 2.3.3 | Web Integration | React/Firestore/Firebase | Admin Dashboard | N/A | Web | Web | Only admins can see admin dashboard buttons